## Security
| Story | Description | Assigned to | Status
Role based UI visiblity
| ROLE_USER : |  | Abhijeet Sahai | Done
1. User can see Dashboard and Profile Tab
2. User can create and upload profile
3. user can see all the profiles created by him
ROLE_INTERVIEWER :
|  | 1. This user can see Dashboard, Profile and interview Tab | Pranaydeep | Done
2. User can create and update(his) profile.
3. This User can submit interview feedback and update feedback.
ROLE_MANAGER :
|  | 1. This user can see Dashboard, Position,Profile and interview Tab | Swapnil
2. User can create and update(his) profile.
3. This User can submit interview feedback and update feedback.
|  | 4. this user can access position tab and approve particular position |  | Done
ROLE_HR:
|  | 1. This user can see Dashboard, Position,Profile and interview Tab | sudhakar
2. This User can create and update Position.
3. This User can create, update and view all profile.
4. This User can schedule and update interview.
|  | 5. This User can view interview feedback . |  | Done
- ROLE_ADMIN
|  | 1. This user can see Dashboard, Position,Profile, interview and Admin Tab | Pradeep
2. Tis user can access Admin tab and do all admin activities
|  | 3. This User can only see position,profile and interview detail,he will not create or update any of position,profile and interview details. |  | Done

## Interview
Section | Story | Description | Assigned to | Status
Interview Schedule | Schedule interview | 1. HR User can schedule intriview in view Profile or Interview Managment page 2. User can create and Update intrview 3. User not allowed to schdule next round interview till last round feedback submit. 4. Interview schdule date shoude be today onwards 5. Interview media details shoude be maindatory like if skype interview then skype id is mendatory 6. Show only available Interviewer | Deepanker
| Interview Schedule Notification | 1. After interview Schdule we have to notifie candidate and interviewer with Email 2. email message should be well formated with all the interview and candidate details | Pranaydeep
| Modify Schedule interview | TBD
Interview Feedback | Interview Feedback | 1. Interview Role user can fill feedback in interview managment 2. user can search candiate by using location and Jobcode. 3. he will submit detail for scheduled interview only | Vinayak | Done
| view Interview Feedback | 1. HR Role user can view feedback in view profile 2. Interview Role user can view feedback in interview managment | Vinayak | Done
Interview Notification | Interview schedule email | 1. email need to send to HR, candidate and Interviewer 2. Mail sent to Interviewer should contain Resume as an attachment. | Vinayak, Sudhakar
Interview Management | Adding role based data display on Interview Management Page | 1. Show/Hide Select options based on looged in User's Role. 2. If the role is ROLE_INTERVIEWER, Only profiles which are scheduled for the logged in Interviewer, should be displayed. 3. Add a new column in Data table for Interview Progress for the profile. | Deepanker

## Admin Tab
Section | Story | Description | Assigned to | Status
Admin Tab | Assigne roles to user | By default login user get ROLE_USER but Admin can assigne his other role such as ROLE_INTERVIEW,ROLE_HR,ROLE_ADMIN, ROLE_MANAGER
| Create Client | Admin User can create/edit/delete client and Location | Vinayak
| Create Designations | Admin User can create new desgination | sudhakar | Done
| Create/Update Skillsets | Admin User can create new Skillset | Pooja | Done
| Create/Update InterviewRounds | Admin User can create new interview rounds | Hrishikesh | Done

## Custome Directive
Section | Story | Description | Assigned to
FormInput Directive | create custom directive for for div which contain label and Html element | have created custom-directive i.e forminput which i have implemented in the project and its working. By using this directive much of the code is been reduced and now the code is clean and readable | RUTURAJ