## Interview
Story | Description | Assigned To | Status
Interview Schedule | 1. Select interview rounds from dropdown | Vinayak | Done
| 2. Filter interviewers based on their Skillsets (Lead, Developer, etc.) | Sudhakar | Done
| 3. Rescheduling will delete current schedule and create again. | Swapnil
Interview Feedback | 1. Textareas should be bigger and designed properly. / Remove Accordion | Vinayak | Done
| 2. Schedule next round from there itself. |  | Carried To Next Iteration
| 3. Send mails to interviewer and HR. | Vinayak | Done
Interview Management | 1. Remove number of rounds and their feedback and add schedule and feedback button instead. | Deepanker | Done
| 2. Add Progress: Waiting to xx Interview Round and feedback. | Deepanker | Done

## Profile
Story | Description | Assigned To | Status
View Profile | 1. Remove number of rounds and their feedback and add button instead. | Deepanker | Done
| 2. Add Progress: Waiting to xx Interview Round and feedback. | Deepanker | Done

## Reports
Story | Description | Assigned To | Status
Interviews | 1. Generate reports for interviews scheduled.
2. Generate reports for interviews cancelled.

## Admin
Story | Description | Assigned To | Status
UserInfo | 1. Attach skillsets to user while assigning to interview Rounds |  | Done